## Construction Draw Schedule
Construction Draw Schedule – So-Good Apartments
Draw # | Draw Date | Period Start | Period End | Category | Budget Line Item | Original Budget | Billed This Draw | Cumulative Billed | Current % Complete (Item) | Total % Complete (Item) | Remaining Budget | Retainage Held This Draw | Cumulative Retainage Held | Net Payment This Draw | Draw Total (Net) | Project Status
1 | 2023-10-15 | 2023-09-01 | 2023-09-30 | Hard Cost | Site Work & Utilities | 4000000 | 300000 | 300000 | 7.5% | 7.5% | 3700000 | 30000 | 30000 | 270000
1 | 2023-10-15 | 2023-09-01 | 2023-09-30 | Soft Cost | Soft Costs & Fees | 8000000 | 250000 | 250000 | 3.13% | 3.13% | 7750000 | 0 | 0 | 250000
1 | 2023-10-15 | 2023-09-01 | 2023-09-30 | Fee | Developer Fee | 3000000 | 100000 | 100000 | 3.33% | 3.33% | 2900000 | 0 | 0 | 100000
1 | 2023-10-15 | 2023-09-01 | 2023-09-30 | Contingency | Contingency | 4000000 | 50000 | 50000 | 1.25% | 1.25% | 3950000 | 0 | 0 | 50000 | 670000 | Initial mobilization & setup. Site clearing and permits.
2 | 2023-11-15 | 2023-10-01 | 2023-10-31 | Hard Cost | Site Work & Utilities | 4000000 | 700000 | 1000000 | 17.5% | 25% | 3000000 | 70000 | 100000 | 630000
2 | 2023-11-15 | 2023-10-01 | 2023-10-31 | Hard Cost | Structure & Shell | 21000000 | 500000 | 500000 | 2.38% | 2.38% | 20500000 | 50000 | 50000 | 450000
2 | 2023-11-15 | 2023-10-01 | 2023-10-31 | Soft Cost | Soft Costs & Fees | 8000000 | 300000 | 550000 | 3.75% | 6.88% | 7450000 | 0 | 0 | 300000
2 | 2023-11-15 | 2023-10-01 | 2023-10-31 | Fee | Developer Fee | 3000000 | 100000 | 200000 | 3.33% | 6.67% | 2800000 | 0 | 0 | 100000 | 1480000 | Earthwork, initial foundations. Permitting progress.
3 | 2023-12-15 | 2023-11-01 | 2023-11-30 | Hard Cost | Site Work & Utilities | 4000000 | 500000 | 1500000 | 12.5% | 37.5% | 2500000 | 50000 | 150000 | 450000
3 | 2023-12-15 | 2023-11-01 | 2023-11-30 | Hard Cost | Structure & Shell | 21000000 | 1500000 | 2000000 | 7.14% | 9.52% | 19000000 | 150000 | 200000 | 1350000
3 | 2023-12-15 | 2023-11-01 | 2023-11-30 | Hard Cost | MEP & Finishes | 15000000 | 300000 | 300000 | 2% | 2% | 14700000 | 30000 | 30000 | 270000
3 | 2023-12-15 | 2023-11-01 | 2023-11-30 | Soft Cost | Soft Costs & Fees | 8000000 | 200000 | 750000 | 2.5% | 9.38% | 7250000 | 0 | 0 | 200000
3 | 2023-12-15 | 2023-11-01 | 2023-11-30 | Contingency | Contingency | 4000000 | 50000 | 100000 | 1.25% | 2.5% | 3900000 | 0 | 0 | 50000 | 2320000 | Foundations complete. Underground MEP rough-ins.
4 | 2024-01-15 | 2023-12-01 | 2023-12-31 | Hard Cost | Site Work & Utilities | 4000000 | 400000 | 1900000 | 10% | 47.5% | 2100000 | 40000 | 190000 | 360000
4 | 2024-01-15 | 2023-12-01 | 2023-12-31 | Hard Cost | Structure & Shell | 21000000 | 2500000 | 4500000 | 11.9% | 21.43% | 16500000 | 250000 | 450000 | 2250000
4 | 2024-01-15 | 2023-12-01 | 2023-12-31 | Hard Cost | MEP & Finishes | 15000000 | 700000 | 1000000 | 4.67% | 6.67% | 14000000 | 70000 | 100000 | 630000
4 | 2024-01-15 | 2023-12-01 | 2023-12-31 | Soft Cost | Soft Costs & Fees | 8000000 | 200000 | 950000 | 2.5% | 11.88% | 7050000 | 0 | 0 | 200000
4 | 2024-01-15 | 2023-12-01 | 2023-12-31 | Fee | Developer Fee | 3000000 | 150000 | 350000 | 5% | 11.67% | 2650000 | 0 | 0 | 150000 | 3590000 | Podium framing underway. Vertical MEP risers.
5 | 2024-02-15 | 2024-01-01 | 2024-01-31 | Hard Cost | Structure & Shell | 21000000 | 3000000 | 7500000 | 14.29% | 35.71% | 13500000 | 300000 | 750000 | 2700000
5 | 2024-02-15 | 2024-01-01 | 2024-01-31 | Hard Cost | MEP & Finishes | 15000000 | 1000000 | 2000000 | 6.67% | 13.33% | 13000000 | 100000 | 200000 | 900000
5 | 2024-02-15 | 2024-01-01 | 2024-01-31 | Soft Cost | Soft Costs & Fees | 8000000 | 200000 | 1150000 | 2.5% | 14.38% | 6850000 | 0 | 0 | 200000
5 | 2024-02-15 | 2024-01-01 | 2024-01-31 | Contingency | Contingency | 4000000 | 100000 | 200000 | 2.5% | 5% | 3800000 | 0 | 0 | 100000 | 3900000 | Upper floor framing. Exterior sheathing beginning.
6 | 2024-03-15 | 2024-02-01 | 2024-02-29 | Hard Cost | Structure & Shell | 21000000 | 3500000 | 11000000 | 16.67% | 52.38% | 10000000 | 350000 | 1100000 | 3150000
6 | 2024-03-15 | 2024-02-01 | 2024-02-29 | Hard Cost | MEP & Finishes | 15000000 | 1500000 | 3500000 | 10% | 23.33% | 11500000 | 150000 | 350000 | 1350000
6 | 2024-03-15 | 2024-02-01 | 2024-02-29 | Soft Cost | Soft Costs & Fees | 8000000 | 250000 | 1400000 | 3.13% | 17.5% | 6600000 | 0 | 0 | 250000
6 | 2024-03-15 | 2024-02-01 | 2024-02-29 | Fee | Developer Fee | 3000000 | 200000 | 550000 | 6.67% | 18.33% | 2450000 | 0 | 0 | 200000 | 4950000 | Roofing and window installation. MEP rough-in intensive.
7 | 2024-04-15 | 2024-03-01 | 2024-03-31 | Hard Cost | Site Work & Utilities | 4000000 | 300000 | 2200000 | 7.5% | 55% | 1800000 | 30000 | 220000 | 270000
7 | 2024-04-15 | 2024-03-01 | 2024-03-31 | Hard Cost | Structure & Shell | 21000000 | 2500000 | 13500000 | 11.9% | 64.29% | 7500000 | 250000 | 1350000 | 2250000
7 | 2024-04-15 | 2024-03-01 | 2024-03-31 | Hard Cost | MEP & Finishes | 15000000 | 2000000 | 5500000 | 13.33% | 36.67% | 9500000 | 200000 | 550000 | 1800000
7 | 2024-04-15 | 2024-03-01 | 2024-03-31 | Soft Cost | Soft Costs & Fees | 8000000 | 300000 | 1700000 | 3.75% | 21.25% | 6300000 | 0 | 0 | 300000
7 | 2024-04-15 | 2024-03-01 | 2024-03-31 | Contingency | Contingency | 4000000 | 100000 | 300000 | 2.5% | 7.5% | 3700000 | 0 | 0 | 100000 | 4720000 | Interior framing complete, initial drywall hanging. Exterior nearly sealed.
8 | 2024-05-15 | 2024-04-01 | 2024-04-30 | Hard Cost | Structure & Shell | 21000000 | 2000000 | 15500000 | 9.52% | 73.81% | 5500000 | 200000 | 1550000 | 1800000
8 | 2024-05-15 | 2024-04-01 | 2024-04-30 | Hard Cost | MEP & Finishes | 15000000 | 2500000 | 8000000 | 16.67% | 53.33% | 7000000 | 250000 | 800000 | 2250000
8 | 2024-05-15 | 2024-04-01 | 2024-04-30 | Soft Cost | Soft Costs & Fees | 8000000 | 300000 | 2000000 | 3.75% | 25% | 6000000 | 0 | 0 | 300000
8 | 2024-05-15 | 2024-04-01 | 2024-04-30 | Fee | Developer Fee | 3000000 | 200000 | 750000 | 6.67% | 25% | 2250000 | 0 | 0 | 200000 | 4550000 | Drywall finishing, flooring prep. Interior doors & trim.
9 | 2024-06-15 | 2024-05-01 | 2024-05-31 | Hard Cost | Site Work & Utilities | 4000000 | 500000 | 2700000 | 12.5% | 67.5% | 1300000 | 50000 | 270000 | 450000
9 | 2024-06-15 | 2024-05-01 | 2024-05-31 | Hard Cost | Structure & Shell | 21000000 | 1500000 | 17000000 | 7.14% | 80.95% | 4000000 | 150000 | 1700000 | 1350000
9 | 2024-06-15 | 2024-05-01 | 2024-05-31 | Hard Cost | MEP & Finishes | 15000000 | 2500000 | 10500000 | 16.67% | 70% | 4500000 | 250000 | 1050000 | 2250000
9 | 2024-06-15 | 2024-05-01 | 2024-05-31 | Soft Cost | Soft Costs & Fees | 8000000 | 350000 | 2350000 | 4.38% | 29.38% | 5650000 | 0 | 0 | 350000
9 | 2024-06-15 | 2024-05-01 | 2024-05-31 | Contingency | Contingency | 4000000 | 100000 | 400000 | 2.5% | 10% | 3600000 | 0 | 0 | 100000 | 4500000 | Cabinetry, countertops, and painting. Landscaping beginning.
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Hard Cost | Site Work & Utilities | 4000000 | 800000 | 3500000 | 20% | 87.5% | 500000 | 80000 | 350000 | 720000
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Hard Cost | Structure & Shell | 21000000 | 1500000 | 18500000 | 7.14% | 88.1% | 2500000 | 150000 | 1850000 | 1350000
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Hard Cost | MEP & Finishes | 15000000 | 2500000 | 13000000 | 16.67% | 86.67% | 2000000 | 250000 | 1300000 | 2250000
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Soft Cost | Soft Costs & Fees | 8000000 | 1000000 | 3350000 | 12.5% | 41.88% | 4650000 | 0 | 0 | 1000000
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Fee | Developer Fee | 3000000 | 500000 | 1250000 | 16.67% | 41.67% | 1750000 | 0 | 0 | 500000
10 | 2024-07-15 | 2024-06-01 | 2024-06-30 | Contingency | Contingency | 4000000 | 50000 | 450000 | 1.25% | 11.25% | 3550000 | 0 | 0 | 50000 | 5870000 | Fixtures, appliances, and final flooring. Paving for parking.
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Hard Cost | Site Work & Utilities | 4000000 | 300000 | 3800000 | 7.5% | 95% | 200000 | 30000 | 380000 | 270000
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Hard Cost | Structure & Shell | 21000000 | 1000000 | 19500000 | 4.76% | 92.86% | 1500000 | 100000 | 1950000 | 900000
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Hard Cost | MEP & Finishes | 15000000 | 1500000 | 14500000 | 10% | 96.67% | 500000 | 150000 | 1450000 | 1350000
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Soft Cost | Soft Costs & Fees | 8000000 | 1500000 | 4850000 | 18.75% | 60.63% | 3150000 | 0 | 0 | 1500000
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Fee | Developer Fee | 3000000 | 750000 | 2000000 | 25% | 66.67% | 1000000 | 0 | 0 | 750000
11 | 2024-08-15 | 2024-07-01 | 2024-07-31 | Contingency | Contingency | 4000000 | 100000 | 550000 | 2.5% | 13.75% | 3450000 | 0 | 0 | 100000 | 4870000 | Unit punch lists. Common area completion. Final site work.
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Hard Cost | Site Work & Utilities | 4000000 | 200000 | 4000000 | 5% | 100% | 0 | 20000 | 400000 | 180000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Hard Cost | Structure & Shell | 21000000 | 1500000 | 21000000 | 7.14% | 100% | 0 | 150000 | 2100000 | 1350000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Hard Cost | MEP & Finishes | 15000000 | 500000 | 15000000 | 3.33% | 100% | 0 | 50000 | 1500000 | 450000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Soft Cost | Soft Costs & Fees | 8000000 | 3150000 | 8000000 | 39.38% | 100% | 0 | 0 | 0 | 3150000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Fee | Developer Fee | 3000000 | 1000000 | 3000000 | 33.33% | 100% | 0 | 0 | 0 | 1000000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Contingency | Contingency | 4000000 | 150000 | 700000 | 3.75% | 17.5% | 3300000 | 0 | 0 | 150000
12 | 2024-09-15 | 2024-08-01 | 2024-08-31 | Retainage Release | Hard Cost Retainage Release | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 4000000 | 10280000 | Final inspections, COs, closeout, retainage release.