## CapEx Plan
| Verified by Capmatch | [5 empty] | Project Name: | Sandbox Tower II
[7 empty] | Date Created: | 2026-01-19
[7 empty] | Total Units/SF: | 120
Category | Item Description | Priority | Condition | Useful Life (Yrs) | Start Date | Completion Date | Vendor | Estimated Cost | Actual Cost | Variance | Cost/Unit or SF | Inflation Factor | Projected ROI | Payback (Yrs) | Status | Notes
Structural | Roof Replacement (TPO System) | Critical | Poor - End of Life | 20 | 2026-04-01 |  |  | 150000 |  |  |  | 103% |  |  | Planned | Current roof has multiple active leaks. Quote from Apex Roofing.
Site Work | Parking Lot Resurfacing & Striping | Medium | Fair | 10 | 2026-06-15 |  |  | 45000 |  |  |  | 103% |  |  | Planned | Fill cracks and sealcoat. Add accessible spaces.
Interiors | Unit Renovations (Phase 1 - 20 Units) | High | Dated | 15 | 2026-02-01 | 2026-08-01 | Creative Interiors LLC | 240000 |  |  |  | 103% |  |  | In Progress | New LVP flooring, stainless appliances, quartz countertops. Expected $250 premium/unit.
Mechanical | Boiler System Replacement | Critical | Poor | 25 | 2026-09-01 |  |  | 85000 |  |  |  | 103% |  |  | Planned | Original 1990 system. Efficiency rating < 80%.
Electrical | Common Area LED Lighting Retrofit | Low | Functional |  | 2026-03-01 |  |  | 12000 |  |  |  | 103% |  |  | Planned | Energy saving initiative. Estimated 1.5 year payback.
Amenities | Pool Deck Concrete Repair | Medium | Fair - Cracking |  | 2026-05-01 |  |  | 18000 |  |  |  | 103% |  |  | Planned | Tripping hazards noted in annual inspection.
Exterior | Exterior Painting (Full Building) | Medium | Fair - Fading |  | 2027-04-01 |  |  | 95000 |  |  |  | 103% |  |  | Planned | Refresh curb appeal. 7-year cycle.
Mechanical | Elevator Cab Modernization (2 Cabs) | High | Fair | 20 | 2026-10-01 |  |  | 110000 |  |  |  | 103% |  |  | Planned | Cosmetic and control system upgrade. Reduce downtime.
Interiors | Lobby Furniture Refresh | Low | Good |  | 2026-07-01 |  |  | 15000 |  |  |  | 103% |  |  | Planned | Modernize entry experience.
Plumbing | Sump Pump Replacement | Critical | Poor |  | 2026-01-25 |  | Rooter Pro | 4500 | 4800 |  |  | 103% |  |  | Completed | Emergency replacement after heavy rain.
Life Safety | Fire Alarm Panel Upgrade | Critical | End of Life |  | 2026-03-15 |  |  | 28000 |  |  |  | 103% |  |  | Planned | Required for code compliance.
Amenities | Fitness Center Equipment | Low | Fair |  | 2027-01-01 |  |  | 35000 |  |  |  | 103% |  |  | Planned | Add Peloton bikes and new treads.
Site Work | Landscape Irrigation Repair | Medium | Poor |  | 2026-05-01 |  |  | 6000 |  |  |  | 103% |  |  | Planned | Fix broken heads and controller.
Exterior | Window Seal Replacements (South Side) | Low | Fair |  | 2027-06-01 |  |  | 22000 |  |  |  | 103% |  |  | Planned | Fogged glass in 15 units.
Marketing | Monument Signage Upgrade | Low | Dated |  | 2026-08-15 |  |  | 12500 |  |  |  | 103% |  |  | Planned | Rebranding with new logo.
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
103%
TOTAL CAPEX: