## Reo Track Record
REO Track Record – So-Good Apartments Development
Date | EventCategory | EventType | ProjectName | Location | UnitCount | Proforma_TotalDevCost | Item_Description | Budget_Cost_Item | Actual_Cost_Item | Budget_Cumulative_DevCost | Actual_Cumulative_DevCost | Variance_Cumulative_DevCost | Loan_Draw_Amount | Loan_Balance_Outstanding | Equity_Injected_Cumulative | Construction_Progress_Pct | Scheduled_Completion_Date | Actual_Completion_Date | Days_Behind_Schedule | Occupancy_Pct | Leased_Pct | Avg_Rent_Achieved | Avg_Rent_Proforma | Risk_Flag | Analyst_Notes
2021-11-15 | Milestone | Land Acquisition | So-Good Apartments | Springfield | 300 | 65000000 | Acquisition of development site | 10000000 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 10000000 | 0 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | Initial equity funded by sponsor, site secured.
2021-12-01 | Financial | Loan Closing | So-Good Apartments | Springfield | 300 | 65000000 | Construction Loan Closing | 0 | 0 | 10000000 | 10000000 | 0 | 0 | 42000000 | 10000000 | 0 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | $42M construction loan closed, 65% LTV on total costs.
2022-01-15 | Milestone | Permit Received | So-Good Apartments | Springfield | 300 | 65000000 | Full Building Permit Received | 0 | 0 | 10500000 | 10000000 | -500000 | 0 | 42000000 | 10000000 | 0 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | Permits obtained on schedule. Initial soft costs accounted for in budget.
2022-02-01 | Milestone | Construction Start | So-Good Apartments | Springfield | 300 | 65000000 | Groundbreaking Ceremony & Site Prep | 500000 | 500000 | 11000000 | 10500000 | -500000 | 0 | 42000000 | 10000000 | 0.01 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | Mobilization and initial site clearing commenced.
2022-03-01 | Construction | Foundation Work | So-Good Apartments | Springfield | 300 | 65000000 | Pouring Foundations | 1500000 | 1500000 | 12500000 | 12000000 | -500000 | 0 | 42000000 | 10000000 | 0.03 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | Foundations progressing well, on budget.
2022-03-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #1 - Site Work & Foundation | 0 | 0 | 12500000 | 12000000 | -500000 | 2000000 | 40000000 | 10000000 | 0.03 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Green | First draw processed, reducing loan commitment.
2022-05-01 | Construction | Framing Progress | So-Good Apartments | Springfield | 300 | 65000000 | Building A & B Framing | 3000000 | 3100000 | 16000000 | 15100000 | -900000 | 0 | 40000000 | 10000000 | 0.1 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Yellow | Slight cost overrun on framing labor. Monitoring closely.
2022-06-01 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #2 - Framing & Sheathing | 0 | 0 | 16000000 | 15100000 | -900000 | 3500000 | 36500000 | 10000000 | 0.1 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Yellow | Draw #2 processed. Variance due to labor cost.
2022-07-15 | Construction | Roofing & Exterior | So-Good Apartments | Springfield | 300 | 65000000 | Roofing & Exterior Cladding | 4000000 | 4200000 | 20000000 | 19300000 | -700000 | 0 | 36500000 | 10000000 | 0.2 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Yellow | Material costs for cladding higher than anticipated.
2022-08-01 | Construction | MEP Rough-in | So-Good Apartments | Springfield | 300 | 65000000 | Mechanical/Electrical/Plumbing Rough-in | 3000000 | 3000000 | 23000000 | 22300000 | -700000 | 0 | 36500000 | 10000000 | 0.3 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Yellow | MEP rough-in on track.
2022-08-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #3 - Roofing & MEP Rough-in | 0 | 0 | 23000000 | 22300000 | -700000 | 4500000 | 32000000 | 10000000 | 0.3 | 2024-03-31 |  | 0 | 0 | 0 | 0 | 2100 | Yellow | Draw #3 released.
2022-09-30 | Issue | Supply Chain Delay | So-Good Apartments | Springfield | 300 | 65000000 | Cabinetry & Appliance Delivery Delay | 0 | 0 | 24000000 | 23000000 | -1000000 | 0 | 32000000 | 10000000 | 0.35 | 2024-03-31 |  | 30 | 0 | 0 | 0 | 2100 | Red | 30-day delay confirmed due to supply chain issues for key finishes. Projected completion date pushed back.
2022-10-15 | Milestone | Schedule Update | So-Good Apartments | Springfield | 300 | 65000000 | Revised Project Schedule | 0 | 0 | 24500000 | 23500000 | -1000000 | 0 | 32000000 | 10000000 | 0.35 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Red | New scheduled completion date of April 30, 2024.
2022-11-01 | Construction | Drywall & Interior | So-Good Apartments | Springfield | 300 | 65000000 | Drywall Installation & Taping | 3000000 | 3200000 | 27500000 | 26700000 | -800000 | 0 | 32000000 | 10000000 | 0.45 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Red | Drywall phase experiencing some labor cost increases.
2022-11-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #4 - Drywall & Interior Rough-in | 0 | 0 | 27500000 | 26700000 | -800000 | 4000000 | 28000000 | 10000000 | 0.45 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Red | Draw #4 released.
2022-12-31 | Construction | Unit Finishes | So-Good Apartments | Springfield | 300 | 65000000 | Installation of Flooring | Paint | Doors | 5000000 | 5300000 | 32500000 | 32000000 | -500000 | 0 | 28000000 | 10000000 | 0.6 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Yellow | Unit finishes progressing, some overrun on flooring due to material cost.
2023-01-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #5 - Unit Finishes & Fixtures | 0 | 0 | 32500000 | 32000000 | -500000 | 5000000 | 23000000 | 10000000 | 0.6 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Yellow | Draw #5 released.
2023-02-28 | Construction | Exterior Landscaping | So-Good Apartments | Springfield | 300 | 65000000 | Landscaping & Hardscaping | 2000000 | 2100000 | 34500000 | 34100000 | -400000 | 0 | 23000000 | 10000000 | 0.7 | 2024-04-30 |  | 30 | 0 | 0 | 0 | 2100 | Yellow | Minor overrun on landscaping, but progress is good.
2023-03-31 | Issue | Weather Delay | So-Good Apartments | Springfield | 300 | 65000000 | Unfavorable Weather Impact on Exterior | 0 | 0 | 35000000 | 34500000 | -500000 | 0 | 23000000 | 10000000 | 0.75 | 2024-04-30 |  | 45 | 0 | 0 | 0 | 2100 | Red | Additional 15 days delay due to persistent rain, impacting exterior work. Scheduled completion updated to May 15, 2024.
2023-04-15 | Milestone | Schedule Update | So-Good Apartments | Springfield | 300 | 65000000 | Revised Project Schedule | 0 | 0 | 35500000 | 35000000 | -500000 | 0 | 23000000 | 10000000 | 0.75 | 2024-05-15 |  | 45 | 0 | 0 | 0 | 2100 | Red | New scheduled completion date of May 15, 2024.
2023-04-30 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #6 - Exterior Finishes & Utilities | 0 | 0 | 35500000 | 35000000 | -500000 | 5500000 | 17500000 | 10000000 | 0.75 | 2024-05-15 |  | 45 | 0 | 0 | 0 | 2100 | Red | Draw #6 released. Lender expressed concern on delays.
2023-06-01 | Construction | Amenities Completion | So-Good Apartments | Springfield | 300 | 65000000 | Clubhouse & Pool Area Completion | 4000000 | 4300000 | 39500000 | 39300000 | -200000 | 0 | 17500000 | 10000000 | 0.85 | 2024-05-15 |  | 45 | 0 | 0 | 0 | 2100 | Yellow | Amenities completed with minor cost overrun.
2023-06-15 | Milestone | CO Phase 1 | So-Good Apartments | Springfield | 300 | 65000000 | Certificate of Occupancy - Building A (100 units) | 0 | 0 | 39500000 | 39300000 | -200000 | 0 | 17500000 | 10000000 | 0.88 | 2024-05-15 | 2023-06-15 | 45 | 0 | 0 | 0 | 2100 | Red | First CO received, 30 days later than revised schedule. Lease-up starting.
2023-07-01 | Leasing | Lease-up Report | So-Good Apartments | Springfield | 300 | 65000000 | Lease-up Building A | 0 | 0 | 40000000 | 39800000 | -200000 | 0 | 17500000 | 10000000 | 0.88 | 2024-05-15 | 2023-06-15 | 45 | 0.05 | 0.1 | 2050 | 2100 | Red | 5% occupied, 10% leased in Building A. Below proforma lease-up pace.
2023-07-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #7 - Final Construction (Phase 1) | 0 | 0 | 40000000 | 39800000 | -200000 | 6000000 | 11500000 | 10000000 | 0.88 | 2024-05-15 | 2023-06-15 | 45 | 0.05 | 0.1 | 2050 | 2100 | Red | Draw #7 released. Concern raised on slow lease-up.
2023-08-01 | Leasing | Lease-up Report | So-Good Apartments | Springfield | 300 | 65000000 | Lease-up Building A | 0 | 0 | 40500000 | 40300000 | -200000 | 0 | 11500000 | 10000000 | 0.9 | 2024-05-15 | 2023-06-15 | 45 | 0.12 | 0.2 | 2025 | 2100 | Red | 12% occupied, 20% leased in Building A. Rents slightly below proforma. Increased concessions.
2023-09-01 | Milestone | CO Phase 2 | So-Good Apartments | Springfield | 300 | 65000000 | Certificate of Occupancy - Building B (100 units) | 0 | 0 | 41000000 | 40800000 | -200000 | 0 | 11500000 | 10000000 | 0.95 | 2024-05-15 | 2023-09-01 | 105 | 0.12 | 0.2 | 2025 | 2100 | Red | CO for Building B delayed. 105 days total delay from original schedule.
2023-09-15 | Financial | Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #8 - Construction (Phase 2) | 0 | 0 | 41000000 | 40800000 | -200000 | 6000000 | 5500000 | 10000000 | 0.95 | 2024-05-15 | 2023-09-01 | 105 | 0.12 | 0.2 | 2025 | 2100 | Red | Draw #8 released. Loan nearing full funding. Lender requesting cash flow projections due to delays/lease-up.
2023-10-01 | Leasing | Lease-up Report | So-Good Apartments | Springfield | 300 | 65000000 | Lease-up Building A & B | 0 | 0 | 41500000 | 41300000 | -200000 | 0 | 5500000 | 10000000 | 0.95 | 2024-05-15 | 2023-09-01 | 105 | 0.18 | 0.3 | 2000 | 2100 | Red | 18% occupied, 30% leased across Buildings A & B. Concessions increasing, effective rents lower.
2023-11-01 | Milestone | CO Phase 3 | So-Good Apartments | Springfield | 300 | 65000000 | Certificate of Occupancy - Building C (100 units) | 0 | 0 | 42000000 | 41800000 | -200000 | 0 | 5500000 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.18 | 0.3 | 2000 | 2100 | Red | Final CO obtained 145 days behind original schedule. Project fully complete physically.
2023-11-15 | Financial | Final Draw Request | So-Good Apartments | Springfield | 300 | 65000000 | Draw #9 - Final Construction (Phase 3) | 0 | 0 | 42000000 | 41800000 | -200000 | 5500000 | 0 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.18 | 0.3 | 2000 | 2100 | Red | Final loan draw completed. Loan balance is now $0, awaiting stabilization. Actual cumulative dev cost $41.8M, budget $42M on loan side.
2023-12-01 | Leasing | Lease-up Report | So-Good Apartments | Springfield | 300 | 65000000 | Full Project Lease-up | 0 | 0 | 42000000 | 41800000 | -200000 | 0 | 0 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.25 | 0.4 | 1980 | 2100 | Red | Lease-up accelerating but effective rents significantly below proforma due to high concessions and slower market.
2024-01-01 | Reporting | Lender Review | So-Good Apartments | Springfield | 300 | 65000000 | Monthly Performance Review | 0 | 0 | 42000000 | 41800000 | -200000 | 0 | 0 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.35 | 0.5 | 1950 | 2100 | Red | Lender expressing significant concern over lease-up pace and achieved rents. Equity shortfall likely.
2024-02-01 | Leasing | Lease-up Report | So-Good Apartments | Springfield | 300 | 65000000 | Full Project Lease-up | 0 | 0 | 42000000 | 41800000 | -200000 | 0 | 0 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.45 | 0.6 | 1920 | 2100 | Red | Still behind proforma. Stabilized Net Operating Income projections are 15% below initial underwriting.
2024-03-01 | Reporting | Sponsor Communication | So-Good Apartments | Springfield | 300 | 65000000 | Sponsor provided updated proforma | 0 | 0 | 42000000 | 41800000 | -200000 | 0 | 0 | 10000000 | 1 | 2024-05-15 | 2023-11-01 | 145 | 0.55 | 0.68 | 1900 | 2100 | Red | Sponsor's updated proforma shows extended lease-up period and lower stabilized rents. Potential for sponsor equity call or debt restructuring required.