## Development Budget
Development Budget – So-Good Apartments
Category | Sub-Category | Description | Unit | Quantity | Unit_Cost | Total_Cost | Percentage_of_Total_Project_Cost | Budget_Line_Item_Code | Notes
Land Costs | Acquisition | Land Purchase | Acre | 5 | 1 | 560 | 0 | 7 | 800 | 0 | 12% | 1010-01 | Acquisition of 5 acres in Springfield.
Land Costs | Closing Costs | Legal & Title Fees | LS | 1 |  | 200 | 0 | 0.31% | 1010-02 | Title insurance | escrow fees | recording fees.
Hard Costs | Site Work & Utilities | Demolition & Grading | LS | 1 |  | 1 | 200 | 0 | 1.85% | 2010-01 | Clearing of existing structures and initial site preparation.
Hard Costs | Site Work & Utilities | Underground Utilities | LS | 1 |  | 2 | 800 | 0 | 4.31% | 2010-02 | Installation of water | sewer | electric | gas | and storm drainage lines.
Hard Costs | Foundations | Concrete & Footings | SqFt | 100000 | 20 | 2 | 0 | 0 | 3.08% | 2020-01 | Concrete slabs and footings for all building structures.
Hard Costs | Structure | Building Framing | Unit | 300 | 36 | 666.67 | 11 | 0 | 0 | 16.92% | 2030-01 | Structural framing (wood or steel) for 300 apartment units.
Hard Costs | Building Envelope | Roofing & Exterior Walls | SqFt | 150000 | 46.67 | 7 | 0 | 0 | 10.77% | 2040-01 | Roofing systems | exterior siding | windows | and exterior doors.
Hard Costs | Interiors | Unit Finishes | Unit | 300 | 25 | 0 | 7 | 500 | 0 | 11.54% | 2050-01 | Drywall | paint | flooring | cabinets | countertops | and fixtures per unit.
Hard Costs | MEP Systems | HVAC | Electrical | Plumbing | Unit | 300 | 16 | 666.67 | 5 | 0 | 0 | 7.69% | 2060-01 | Installation of mechanical | electrical | and plumbing systems for all units.
Hard Costs | Common Areas & Amenities | Clubhouse | Pool | Landscaping | LS | 1 |  | 2 | 0 | 0 | 3.08% | 2070-01 | Finishes for clubhouse | fitness center | pool construction | and exterior landscaping.
Hard Costs | General Conditions | Supervision & Site Office | Month | 24 | 104 | 166.67 | 2 | 500 | 0 | 3.85% | 2080-01 | Construction management | site supervision | temporary facilities | and security for 24 months.
Soft Costs | Architectural & Design | Architectural Services | LS | 1 |  | 1 | 500 | 0 | 2.31% | 3010-01 | Schematic design | design development | and construction documents.
Soft Costs | Architectural & Design | Interior Design | LS | 1 |  | 300 | 0 | 0.46% | 3010-02 | Selection and specification of interior finishes and FF&E for units and common areas.
Soft Costs | Architectural & Design | Landscape Design | LS | 1 |  | 200 | 0 | 0.31% | 3010-03 | Design for exterior common areas | planting | and hardscapes.
Soft Costs | Engineering | Civil Engineering | LS | 1 |  | 400 | 0 | 0.62% | 3020-01 | Site plans | grading | drainage | and utility infrastructure design.
Soft Costs | Engineering | Structural Engineering | LS | 1 |  | 300 | 0 | 0.46% | 3020-02 | Design and analysis of building structural systems.
Soft Costs | Engineering | MEP Engineering | LS | 1 |  | 300 | 0 | 0.46% | 3020-03 | Design of HVAC | electrical power | lighting | and plumbing systems.
Soft Costs | Legal & Admin | Legal Fees | LS | 1 |  | 500 | 0 | 0.77% | 3030-01 | Legal services for entitlement | acquisition | financing | and corporate matters.
Soft Costs | Permits & Fees | Building Permits | LS | 1 |  | 1 | 0 | 0 | 1.54% | 3040-01 | Fees for obtaining all necessary building permits from municipal authorities.
Soft Costs | Permits & Fees | Impact Fees & Utilities Connections | LS | 1 |  | 500 | 0 | 0.77% | 3040-02 | Fees for increased demand on public services (schools | roads) and utility hook-ups.
Soft Costs | Surveys & Environmental | Surveys & Geotech | LS | 1 |  | 150 | 0 | 0.23% | 3050-01 | Topographic | boundary | ALTA surveys | and geotechnical soil investigations.
Soft Costs | Surveys & Environmental | Environmental Studies | LS | 1 |  | 100 | 0 | 0.15% | 3050-02 | Phase I and potentially Phase II Environmental Site Assessments.
Soft Costs | Appraisal & Market | Appraisal & Market Study | LS | 1 |  | 100 | 0 | 0.15% | 3060-01 | Third-party property valuation and market demand analysis.
Soft Costs | Insurance & Taxes | Builder's Risk & GL Insurance | Month | 24 | 16 | 666.67 | 400 | 0 | 0.62% | 3070-01 | Property and general liability insurance coverage during the construction phase.
Soft Costs | Insurance & Taxes | Property Taxes (during construction) | Month | 24 | 12 | 500 | 300 | 0 | 0.46% | 3070-02 | Property taxes on the land and partially completed improvements during development.
Soft Costs | Marketing & Leasing | Marketing Materials & Website | LS | 1 |  | 300 | 0 | 0.46% | 3080-01 | Development of branding | brochures | website | and promotional content.
Soft Costs | Marketing & Leasing | Leasing Commissions & On-site Staff | LS | 1 |  | 700 | 0 | 1.08% | 3080-02 | Commissions for leasing agents and expenses for temporary on-site leasing staff during lease-up.
Soft Costs | Developer Fee | Developer Fee | LS | 1 |  | 3 | 0 | 0 | 4.62% | 3090-01 | Compensation for the developer's expertise | project oversight | and risk.
Soft Costs | Project Management | Owner's Rep / Project Management | Month | 24 | 39 | 583.33 | 950 | 0 | 1.46% | 3100-01 | Internal project management and oversight provided by the developer's team.
Financing Costs | Loan Fees | Loan Origination Fee | % | 2.5 | 52 | 0 | 0 | 1 | 300 | 0 | 2% | 4010-01 | Fee paid to the construction lender at loan closing (2.5% of $52M assumed loan).
Financing Costs | Loan Fees | Lender Legal & Admin | LS | 1 |  | 200 | 0 | 0.31% | 4010-02 | Lender's legal counsel fees and administrative costs for loan setup.
Financing Costs | Interest During Construction | Interest Reserve | Month | 24 | 41 | 666.67 | 1 | 0 | 0 | 1.54% | 4020-01 | Funds reserved to cover interest payments on the construction loan during the development period.
Contingency | Project Contingency | Owner's Project Contingency | % | 3.85 |  | 2 | 500 | 0 | 3.85% | 5010-01 | Reserve for unforeseen costs | changes in scope | or budget overruns during the project.